## Sheet1
Milestones
TODO
Week | Goal | Achieved | Delay | Requirements:
Make Enemy Move
9 | Start | --- | --- | Enemy | Spawn | Make Enemy Move from A to B
10 | Enemies |  | yes |  | Type | Make Enemy Spawn at A, go to B then die at C
11 | Towers |  |  |  | Speed | Create "Round" system to spawn waves of enemies
12 | UI |  |  |  | HP
13 | Polish |  |  |  | Destroy | Create Grid for tower placement
Create basic tower that shoots at enemy
|  |  |  | Tower | Spawn | Build Mode vs Attack Mode
[5 empty] | LookAtEnemy | Basic Build/Attack UI
Shoot
Multiple Enemies & Towers (min 2)
|  |  |  | GameState | Build | Tower Upgrades
[5 empty] | Attack | Main Menu
[5 empty] | Menu | Pause Menu
|  |  |  | UI | Main Menu
Build UI
Attack UI
Persistent UI
Pause Menu